## Project Summary
Metric | Value
Project | AI Support Operations SLA Breach & Priority Triage
Dataset Size | 15,000 records
Target | sla_breached
Breach Rate | 60.9%
Best Model | Gradient Boosting
Precision | 0.892
Recall | 0.913
F1 Score | 0.903
ROC-AUC | 0.961
Threshold | 0.50
Recommendation | Further validation using real-world data

## Risk Register
Risk ID | Risk Area | Description | Likelihood | Impact | Severity | Mitigation | Owner | Status | Evidence
R001 | Data Leakage | Post-resolution columns may inflate model performance. | High | High | High | Exclude leakage columns. | Jumma Mohammad | Closed | Feature Engineering Notebook
R002 | Data Quality | Missing values, duplicates and category inconsistencies. | Medium | High | High | Cleaning and imputation. | Jumma Mohammad | Closed | Data Cleaning Notebook
R003 | Overreliance | Users may rely on predictions without review. | Medium | High | High | Human review process. | Jumma Mohammad | Open | Model Card
R004 | Representation | Synthetic data may not represent all groups. | Medium | Medium | Medium | Validate on real data. | Jumma Mohammad | Open | EDA + Evaluation
R005 | Model Drift | Ticket patterns may change over time. | Medium | Medium | Medium | Monitoring and retraining. | Jumma Mohammad | Open | Monitoring Plan
R006 | Synthetic Dataset | Performance may not generalise to production. | High | High | High | Validate using production data. | Jumma Mohammad | Open | Final Recommendation

## Assumptions
ID | Assumption | Why It Matters | Evidence | Status
A001 | Prediction occurs before resolution | Defines valid features | Feature list | Confirmed
A002 | SLA breach is a useful business target | Supports model value | Business problem | Confirmed
A003 | Synthetic data suitable for learning | Limits deployment claims | Dataset description | Accepted
A004 | Business values recall over missed breaches | Supports threshold choice | Threshold analysis | Confirmed

## Controls
Control ID | Control | Related Risk | Evidence | Completed
C001 | Remove leakage features | R001 | Feature Engineering | Yes
C002 | Document cleaning decisions | R002 | Cleaning Notebook | Yes
C003 | Report evaluation metrics | R003 | Evaluation Notebook | Yes
C004 | Create model card | R003 | Model Card | Yes
C005 | Define monitoring process | R004/R005 | Final Report | Yes